## Sheet1
Team | Defect Type | Defect ID | Status | Summary | Initiative | Priority | Resolution Comments | Remedy Ticket# | County
Team 1 | Functional | 57693 | Ready for UAT | IV13a - Clear incomplete dispositions on pathway switch |  | 2-High | NCANDS errors revealed that some intakes were completed with both Alternative Response and Traditional disposition values. This happens when a user enters AR dispositions on some allegations, then completes a pathway switch, then enters the remaining dispositions. To prevent this error, the pathway switch functionality will clear the disposition on all allegations for the affected screened in AR intake(s). |  | 00--State
Team 1 | Functional | 58545 | Ready for UAT | CF45 - Maintain Tribe Information enhancements | AFCARS | 5-Change/Enhancement | Information on each federally recognized American Indian and Alaskan Native tribe is maintained by state users. The Tribe Information screen will now include a field to store the EPA code for the tribe, which will be used for AFCARS reporting. |  | 00--State
Team 1 | Functional | 58595 | Ready for UAT | CF45- Add EPA Code to Tribe Search Screen | AFCARS | 5-Change/Enhancement | The EPA code will be added to the Tribe Search criteria. This functionality is accessed / maintained by state users. |  | 00--State
Team 1 | Functional | 59684 | Ready for UAT | PM01b- Add Validation to Pregnancy/Parenting tab | AFCARS | 5-Change/Enhancement | For AFCARS initiative, a new question is being added to the Pregnancy/Parenting tab in the Person Medical module: Has this person ever fathered or given birth to any children? When there is at least one Pregnancy Details record (excluding created in error) with an Outcome value of “Live Birth,” “Surrendered for Adoption,” or “Neonatal Death,” the question, will be set to Yes and disabled. If Pregnancy Detail record(s) are updated such that the above condition is not met, the field will remain set to yes, but will be enabled. |  | 00--State
Team 2 | Functional | 59699 | Ready for UAT | CM07 Update Reference Value Custody Relinquishment and Initial Removal Validations | AFCARS | 5-Change/Enhancement | Due to the AFCARS Initiative updates, the Initial Removal Reason of Custody Relinquishment - Treatment has been updated. These two new reference values are Custody Relinquishment – Medical Treatment and Custody Relinquishment – Mental Health Treatment. If one or both of these removal reasons has been selected, they are the only available Primary Removal Reasons available for selection.
Team 2 | Functional | 59743 | Ready for UAT | CM61 - OhioKAN Basics values for PASSS cases | PASSS State Design | 5-Change/Enhancement | Allow users to select PASSS as reason for completion for all new BASICS questionnaires.
Team 2 | Functional | 58664 | Ready for UAT | CM07 Initial Removal AFCARS Element 71 Environment at Removal dropdown | AFCARS | 5-Change/Enhancement | Based on the Federal AFCARS 2020 updates, the system will display the AFCARS Element #71 Environment at Removal to the Initial Removal page. This is a required field and the values include: Parent Household, Relative Household, Legal Guardian Household, Relative Legal Guardian Household, Justice Facility, Medical / Mental Health Facility, and Other.
Team 2 | Warranty | 59571 | Ready for UAT | CM05b- Children are not Appearing in the Candidate Foster Care Tab on Family Case Plan |  | 2-High | Candidate for Foster Care tab will no longer display if case particpants are reimbursable for Prevention Services. | 00407537 | 23--Fairfield
Team 2 | Functional | 55765 | Ready for UAT | CM07 Initial Removal AFCARS Updates | AFCARS | 5-Change/Enhancement | Based on the Federal AFCARS 2020 updates, the system will display the two (2) new Radio Buttons for the AFCARS Elements 72 and 73. This will display when the AWOL at Removal has been selected. ( ) Child is consider a Runaway ( ) Child's whereabouts unknown but not consider a Runaway In addition, numerous Initial Removal Reasons have been added for AFCARS Reporting.
Team 2 | Functional | 59650 | Ready for UAT | CM64- Bridges Ongoing Eligibility Error After Person Merge |  | 2-High | Fix to correct Bridges Ongoing Eligibility records for merged person records. |  | 00--State
Team 2 | Functional | 59651 | Ready for UAT | CM56- Bridges Application Error After Person Merge |  | 2-High | Fix to correct Bridges Application records for merged person records. |  | 00--State
Team 2 | Functional | 60014 | Ready for UAT | CM05b - SSA cannot remove approval on case plan when worker/supervisor signature recorded |  | 3-Medium | SSAs did not previously have the ability to remove approval from a Family Case Plan if a Supervisor or Caseworker signature had been recorded. This has been fixed and SSAs are now able to remove Family Case Plan approval when Caseworker or Supervisor signature is recorded. | 448567
Team 2 | Functional | 60283 | Ready for UAT | CM64 - Unable to access attached documents |  | 3-Medium | Fix to allow for viewing/download of uploaded documents within Bridges Ongoing Eligibility. | 461992 | 00--State
Team 2 | Functional | 60388 | New | CM07 Initial Removal AFCARS Updates | AFCARS | 5-Change/Enhancement | The following Removal Reasons on Initial Removal have been deactivated: Child Drug Affected (Child Effected by Substance Abuse) Sibling Removal Child of Minor Parent Dependency
Team 2 | Functional | 60537 | Ready for UAT | CM07 Java Error Recieved when View link is clicked | AFCARS | 1-Critical | The system was displaying a Java Error when View link is clicked on an Initial removal record. This has been fixed and the error is no longer displayed.
Team 2 | Functional | 60559 | Ready for UAT | CM09 Placement Access displays Java Error |  | 1-Critical | The system was displaying a Java Error when accessing a Placement record. This error has been fixed and is no longer displayed.
Team 3 | Functional | 58661 | Ready for UAT | CM20b Adoption Case Inactivation AFCARS Element Requires Sibling Relationship Verification | AFCARS | 5-Change/Enhancement | Based on the Federal AFCARS 2020 updates, the system will now require Sibling Relationship Verification for every Adoption Case Member when they are Inactivated.
Team 3 | Functional | 58662 | Ready for UAT | CM20g Adoption Seal/Secure AFCARS Element 56 Validation | AFCARS | 5-Change/Enhancement | Based on the Federal AFCARS 2020 updates, the system will now require Sibling Relationship Verification for the child at the time of Seal / Secure.
Team 3 | Functional | 59219 | Ready for UAT | AFCARS:RM02 Synchronizing Provider/Person Martial Stautus information | AFCARS | 5-Change/Enhancement | A static message will displays on the Member Tab for Household Maritial Status. Message: Check Person Marital staus information for provider member when updating House martial status. A Notification is being sent when Maritial Status has been change.
Team 3 | Functional | 59254 | Ready for UAT | RM02 - Address Validation | AFCARS | 5-Change/Enhancement | New validation message for Address. At least one current address with 'Physical' or 'Residence' type and valid (not 'unknown') address exists for this provider. This validation will be executed for Home providers on Apply/Save click from any Provider Information tab |  | 00--State
Team 3 | Warranty | 60651 | New | RM48e - Safety Hazard narrative converts text | QRTP - Phase 2 | 4-Low | RTIS Safety Hazaed narrative no longer converts text data. |  | 00--State
Team 4 | Functional | 54786 | Ready for UAT | CF24 - Agency Information |  | 2-High | Issue preventing MCP Coordinators and MCP Portal Coordinators has been resolved. Agencies can now add their own Coordinators under Agency Information | 00118697 | 13--Clermont
Team 4 | Functional | 55585 | Ready for UAT | Agency Information |  | 3-Medium | Agencies can now end date Agency Configuration records if the associated employee has a job (past or present) that is within with the begin/end date of the configuration record. | 00136640 | 25--Franklin
Team 5 | Functional | 39607 | Ready for UAT | FM33 - disrupted adoptive children not displaying correctly in Part 3 and Part 5 | 4280/4281 Enhancements | 4-Low | Children with disrupted adoptions will display correctly in Part 3 and part 5 of Statistical Reporting.
Team 5 | Functional | 59640 | Ready for UAT | FM41 - OhioSTART services need to accept partial units |  | 3-Medium | OhioSTART functionality can accept partial units.
Team 5 | Functional | 60562 | Ready for UAT | FM34 - PASSS State Notification - 24 hour | PASSS State Design | 3-Medium | PASSS state workes will receive notifications 24 hours in advance.
Team 5 | Functional | 60563 | Ready for UAT | CF24 - MCP Portal Coordinator updates |  | 5-Change/Enhancement | Person Search will be available to the portal.
Team 5 | Functional | 60570 | Ready for UAT | FM34 - SFY does not update once selected | PASSS State Design | 3-Medium | State Fiscal Year will be updated upon selection.
Team 5 | Functional | 60595 | Ready for UAT | FM34 - OhioKAN security is incorrect in production | PASSS State Design | 3-Medium | OhioKAN security will be set in Production.
Team 5 | Functional | 60642 | Ready for UAT | FM34 - PASSS draft and pending time stamp needs update to 24hr time | PASSS State Design | 3-Medium | PASSS draft and the pending time stamp will be updated to 24 hour time.
Team 5 | Functional | 60323 | Ready for UAT | FM34 - Denial does not set pending inital review to complete | PASSS State Design | 2-High | PASSS denials will send the initial review to Pending status.
Team 5 | Functional | 60324 | Ready for UAT | FM34 - System does not set Denied applications with a sustained appeal back to pending. | PASSS State Design | 2-High | Denied applications with sustained appeals will be set back to pending.
Team 5 | Functional | 60335 | Ready for UAT | FM34 - Add PASSS Specifc Provider Search | PASSS State Design | 3-Medium | Provider search will be added to PASSS.
Team 5 | Functional | 60357 | Ready for UAT | CF24 - MCP Portal Coordinator error when entering |  | 3-Medium | This will resolve the error users receive when entering the portal.
Team 5 | Functional | 60371 | Ready for UAT | FM15a - QRTP flag = 0 on QRTP Reversed State Payments in Production and UAT | QRTP - Phase 2 | 3-Medium | This defect is to ensure that all payments, whether they are positive or negative, are appropriately identified when they are QRTP.
Team 5 | Functional | 60373 | Ready for UAT | FM15a - State Payment was not created on a Congregate Care Placement Setting Payment Request | QRTP - Phase 4 | 3-Medium | State payments will be created for every payment request for a congregate care setting.
Team 5 | Functional | 60153 | Ready for UAT | FM20a - PCE not being created when Reimbursability record completed in UAT | QRTP - Phase 4 | 2-High | Payment change events will be created when a reimbursability record is saved.
Team 5 | Functional | 60813 | Fixed | FM17 - Unable to execute CB496 Statistical Report |  | 4-Low | This defect is to fix the issue that is preventing state users to run the CB-496 Statistical Report.
Team 5 | Functional | 59989 | Ready for UAT | FM22a - Add MCP Enrollment/Disenrollment button should not be disabled for counties when child is placed out of state |  | 5-Change/Enhancement | When a child is placed out of state the Add MCP Enrollment/Disenrollment button will be enabled.
Team 6 | Online Report | 59876 | Rework | RPT539_CPOE_Substitute_Care_Report - Report column additions: Request to add two (2) new columns to Rpt 539 CPOE Substitute Care Report |  | 3-Medium | Two (2) new columns have been added to report for: (1) Child's Age and (2) Length of time (in Days) Case has been Open During the Selected Time Frame.
Team 6 | Online Report | 59877 | Assigned | RPT540_CPOE_In_Home_Report - Report column additions: Request to add three (3) new columns to Rpt 540 CPOE In-Home Report |  | 3-Medium | Three (3) new columns have been added to the report for: (1) Active Safety Plan in place during the selected time frame, (2) Accepted maltreatment report during the selected time frame, and (3) Length of time (in days) the case has been open during the selected time frame