## Release Notes
Team/ Functional Area | Defect ID | Ticket # | Source County | Report ID | Report Name | Summary of Defect | Resolution Comments
Change/Enhancement Defects or New Functionality
Intake Management - Person (Team 1) | 33117 |  |  |  |  | ADDRESS TABLE CHANGE | Latitude and longitude are being added to the address table, as address broker now supplies this information. This data does not display in the application at this time, but may have future utility.
Intake Management - Person (Team 1) | 31714 |  | 00--State | 13 | Intake Worksheet (Version A - D) | RPT 013- Intake Worksheet Redesign | The Intake Worksheet report has been updated to incorporate field changes as a result of the intake usability redesign.
Intake Management - Person (Team 1) | 32745 |  |  |  |  | PM01b- Clean up validation message | On Person>Medical>Health Care Provider Information page, there is a validation to ensure Provider End Date is not earlier than the First Visit date. The message has been edited for clarity: "Provider End Date cannot be earlier than First Visit."
Intake Management - Person (Team 1) | 31167 |  |  |  |  | CF56- Create New Global Navigation | A new Recent button (next to Home) now displays a list of the recent cases, intakes, persons, inquiries, and providers which the logged in user has accessed, either in view or edit mode.
Intake Management - Person (Team 1) | 31169 |  | 00--State |  |  | IN03- Screening Decision Changes for Intake Usability | Redesign of the Intake Screening Decision functionality. Decision comments have been moved off the decision tab so they may be saved prior to saving the screening decision. Fields on the decision tab display as applicable, based on the information given. Reason for not screening in AR is auto-populated when possible. A confirmation screen displays a summary of the key intake and decision information upon save of the decision to give the SDM an opportunity to go back and make corrections if needed.
Intake Management - Person (Team 1) | 30430 |  |  |  |  | IN07 - Add validation message when user deletes or deactivates a Case Member | Validation message has been added that displays when a user attempts to deactivate a Case Member if there is an Active or Pending IL Plan, non-end-dated Final Transition Plan or a non-end-dated Emancipated Youth Plan.
Intake Management - Person (Team 1) | 31354 |  |  | 29 | Law Enforcement Notification Report | RPT 029- Add field to Law Enforcement Notification Report parameters | A ‘Comments’ character field has been added to the parameter page that includes character counter, spell check, and clear buttons.
Intake Management - Person (Team 1) | 31355 |  | 00--State | 32 | Law Enforcement Request for Assistance | RPT 032- Add field to Law Enforcement Request for Assistance parameters | A ‘Comments’ character field has been added to the parameter page that includes character counter, spell check, and clear buttons.
Intake Management - Person (Team 1) | 31356 |  |  | 29 | Law Enforcement Notification Report | RPT 029- Update data source for Law Enforcement Notification report | The ‘Comments" character field has been moved to the report parameter page, therefore report has been updated to capture the comments from the new location.
Intake Management - Person (Team 1) | 31357 |  | 00--State | 32 | Law Enforcement Request for Assistance | RPT 032- Update data source for Law Enforcement Request for Assistance report | The ‘Comments" character field has been moved to the report parameter page, therefore report has been updated to capture the comments from the new location.
Intake Management - Person (Team 1) | 30026 |  |  |  |  | IN01- Intake Category Change Screen | When user changes the Intake Category, an interim page displays with a warning message to confirm changes to allegations and/or roles.
Intake Management - Person (Team 1) | 30639 |  |  |  |  | IN07 - Case Participant Merge for IL, FT, and EY Plans | If there is an Active or Pending IL Plan for the removed Case Member, the system will not allow Case Participant Merge. The user will receive a validation message "The Removed Case Member has an Active/Pending Independent Living Plan."
Intake Management - Person (Team 1) | 30642 |  |  |  |  | IN07 - Correct Person ID Rules for IL, EY, and FT Plans | Person ID on IL, EY and FT plans have been changed to the person ID that has been identified as the Correct person ID when the State System Admin. utility is used.
Intake Management - Person (Team 1) | 28875 |  |  |  |  | IV22 - Missing Validation for Required Disposition Changed Date | When changing an intake disposition, the 'Disposition Changed Date' is marked as required, but this was not being enforced. The system will now validate that this information is complete rather than auto-populating with the system date.
Intake Management - Person (Team 1) | 28402 | 0050266 | 25--Franklin |  |  | IN01- Add designation and drug type values to intake | A value of Substance Use &/or Activity was added to the Other Designations list; MDMA (AKA X, Ecstasy, Molly) has been added to the Drug Types list.
Intake Management - Person (Team 1) | 29457 |  | 00--State |  |  | IV18- Add Intake and Case Hyperlinks to Linking Confirmation Message | On the confirmation message for linking an intake to a case, the intake ID and the case ID are now hyperlinks to those records.
Intake Management - Person (Team 1) | 29143 |  |  |  |  | IN10- Add Relationship to Related Persons Display | When you click on the related persons link beneath a person's name, the grid that displays now includes the relationships of the related persons to the focus person.
Intake Management - Person (Team 1) | 29196 |  |  |  |  | IN12- Intake Workload Decision Timeliness Indicator | When an intake on the intake workload does not have a screening decision completed and time since received date/time is greater than or equal to 22 hours, the Screening Priority column displays "High," regardless of the priority selected within the intake, including when the screening priority is null. (The screening priority in the intake does not change). Beneath the "High" priority indicator, "hh:mm remaining" displays the time until the 24 hour deadline for screening decision. The label displays in black. But, once the intake has reached 24 hours from received date/time and no time remains, the time remaining displays "00:00" in red. Once a screening decision has been saved, no screening priority or time remaining displays.
Intake Management - Person (Team 1) | 29197 |  |  |  |  | IN12- Intake Workload Enhancements | The following changes have been made to the Intake Workload display: A view hyperlink has been added to the first column on the left. (The intake ID will also remain as a view only hyperlink.) A High, Med, Low screening priority indicator has been added. Display Comments field has been added and shows if comments exist. Otherwise, this row does not display. The far right column contains the following icons: a. Narrative- Click displays lightweight pop up box containing first 1,000 characters of the intake narrative, with 'view full narrative' link that provides a view only path into the intake. b. Copy icon c. (TBD- document attachment icon, pending Document Management initiative) 5. Date/time, screener/SDM name, and status columns are now sortable: ascending/descending
Intake Management - Person (Team 1) | 29577 |  |  |  |  | IN03- Auto-populate Reason for not screening AR | On the screening decision tab, if screened in is selected for the screening decision, then the system auto-fills the "Reason for not screening In AR" field when the information is known to the system rather than requiring the user to select from a drop down. 1. If report is CA/N and the fatality question on the basic tab is Yes, and an ACV has a fatality status of "Fatality," then set the reason to "Mandatory- Report involves a suspicious child fatality or homicide." 2. If report is CA/N and an ACV has a fatality status of "Near Fatality," then set the reason to "Mandatory- Report that alleges serious injury or harm to a child" 3. If Sexual Abuse is an Intake Type, then set reason to "Mandatory- Report alleges sexual abuse of a child" 4. If question on the basic tab pertaining to Specialized Assessment is Yes, then set reason to "Mandatory- A report requiring a specialized assessment" 5. If question on the basic tab pertaining to Third Party involvement is Yes, then set reason to "Mandatory- A report requiring a third party assessment" 6. If the ACV is in the custody of the PCSA, then set reason to "Mandatory- PCSA has custody of child" 7. If the ACV has a legal status of TCOPS or COPS or COPSEXT, then set reason to "Mandatory- PCSA court involved with the family"
Intake Management - Person (Team 1) | 30043 |  |  |  |  | CM30- Auto generated activity log for Law Enforcement Notification | An Activity Log is generated upon save of Law Enforcement Notification and Law Enforcement Request for Assistance Reports. Any comments on the parameter page of the report are added to the Activity Log.
Intake Management - Person (Team 1) | 30051 |  |  |  |  | IN01- Prevent duplicate addresses via Intake Copy | When copying addresses in Intake the system will prevent any duplicate addresses from being added.
Intake Management - Person (Team 1) | 30054 |  |  |  |  | IN01- Intake Usability Redesign Master Defect | A complete redesign of the Intake module has been completed. Changes were informed by a usability study which included a survey, interviews with stakeholders, PCSA site visits, and field observations.
Intake Management - Person (Team 1) | 27115 |  |  |  |  | IN01- Message needed on attempt to remove intake type with allegations | In a pending intake, if user tries to remove an intake type for which there are allegations, an interim page will be displayed with a warning message that the associated allegations will be deleted. The user will have the option to continue or cancel.
Intake Management - Person (Team 1) | 28077 |  |  |  |  | IN03- New Notification to TAM for CA/N Fatality Intake | New email notification to TAMS and Agency System Admins to alert when an intake marked as Fatality or Near Fatality is screened in or out.
Intake Management - Person (Team 1) | 27692 |  |  |  |  | New Notification to TAM for Near/Fatality Dispo | New notification to be sent to the Technical Assistance Managers upon AI Completion if the severity of harm is Near Fatality or Child Fatality or the Intake has been flagged as an alleged fatality or near fatality.
Intake Management - Person (Team 1) | 26142 | 45293 | 25--Franklin |  |  | IN01 - REPORTER- Make type selection dependent on Mandated/Non-Mandated reporter | The Intake Reporter Type drop down lists for Mandated and Non-Mandated have been separated.
Intake Management - Person (Team 1) | 26268 | 45369 | 25--Franklin |  |  | CM49 - Add Narrative Expansions | For the Ongoing A/I Tool 'expand full screen' has been added to all narrative boxes.
Intake Management - Person (Team 1) | 23229 |  |  |  |  | IN01 - Add static message to relationships page | When selecting relationships, a message displays on the screen to remind users to select the most specific relationship value available.
Intake Management - Person (Team 1) | 23076 | 0039545 | 18--Cuyahoga |  |  | IN03 - Show Original SDM name on Intakes where the Screening Decision was changed | For Intake Redesign, Decision Comments and Correction Comments now display with the worker name, date and time of the correction.
Intake Management - Person (Team 1) | 23619 | 0040665 | 77--Summit |  |  | IN03 - Allow Screening Decision Comments to be entered and saved prior to Decision | This requested change/enhancement allows screening decision comments to be entered and saved on a completed intake prior to recording the screening decision.
Intake Management - Person (Team 1) | 19952 | 78170 | 25--Franklin |  |  | IN01 - Intake Participant Details Enhancement | Fields on the intake participant details page have been added to align with the person record.
Intake Management - Person (Team 1) | 21015 | 81899 | 77--Summit |  |  | IN12 - Copy Reporters on Copy Intake Request | When an intake has been copied, all reporters are now copied. The contact date/time for each reporter is also copied forward.
Case Management - (Team 2) | 31727 |  |  |  |  | IL Signatures | New Functionality - Signature page has been added to the IL Plan.
Case Management - (Team 2) | 32951 |  |  |  |  | CM 44 Home Provider Merge | Provider Tables updated to reflect the changes made for Home Provider merge for the IL Plan Initiative.
Case Management - (Team 2) | 32952 |  |  |  |  | CM 44 Non-ODJFS Provider | Provider Tables updated to reflect the changes made to the Non ODJFS Providers for the IL Plan Initiative.
Case Management - (Team 2) | 29563 |  |  |  |  | CM44 - Add Relationship Value to Contact Information on IL Plan - AFCARS | New Functionality - A check box has been added to Contact Directory stating 'Youth has no Permanent Adult Connections' to determine if the contact is a Permanent connection.
Case Management - (Team 2) | 29855 |  |  | 409 | Emancipated Youth Plan Report | New RPT 409 - Create Emancipated Youth Plan Report | New Report- Emancipated Youth Plan (for youth 18-21 who emancipated from PCSA and is requesting services) is now available. EY Plan can only be completed on an Emancipated Youth Case
Case Management - (Team 2) | 29857 |  |  | 408 | Independent Living Plan Summary - Youth Version | New RPT 408 - Create Independent Living Plan - Youth Version | New Report - IL plan-Youth Version (Simplified version of the IL Summary report) is now available.
Case Management - (Team 2) | 29858 |  |  | 407 | Final Transition Plan Report | New RPT 407- Create Final Transition Plan Report | New Report - Final Transition Plan. FT Plan is to be completed within 90 days of a youth emancipating from agency custody.
Case Management - (Team 2) | 30241 |  |  |  |  | CM44- Add additional Reference values IL Plan-Youth Version and Contact | Independent Living Summary Report-Youth Version and Independent Living Contact Report have been added to the dropdown box in Generate Report
Case Management - (Team 2) | 30242 |  |  | 411 | Youth Support Contact Report | New RPT411 Create Independent Living Contact Report | New Report - Contact Directory Report is now available.
Case Management - (Team 2) | 30290 |  |  |  |  | CM01i - Validate upon Court Jurisdiction Transfer for IL, FT, and/or EY Plan | The system no longer allows user to complete a court jurisdiction transfer if there is an active or pending IL plan, a non-end-dated FT plan, and/or a non-end-dated EY plan.
Case Management - (Team 2) | 30293 |  |  |  |  | CM52 - Validate upon Case Transfer for IL, EY and FT Plan | A validation has been added prohibiting a case transfer when there is an active or pending IL plan, a non-end dated Final Transition plan, and/or non-end dated EY Plan.
Case Management - (Team 2) | 30965 |  | 00--State | 349 | Agency Independent Living Summary Report | RPT 349 - Independent Living Summary Report version 2.0 as of 04 05 2016 | New Functionality-Report has been updated with changes/additions/deletions.
Case Management - (Team 2) | 31519 |  |  | 66 | JFS 01412 - SAR Document | IL Initiative Report Impact - RPT 066 - JFS01412 SAR Document | The tables have been updated and corrections made as related to the SAR document.
Case Management - (Team 2) | 31520 |  |  |  |  | IL Changes Application Impacts | Application Impacts have been tested and fixed.
Case Management - (Team 2) | 31530 |  |  | 374A | Permanency Roundtable Skills Case Summary Form A | IL Changes RPT374A Permanency Roundtable Skills Case Summary Form | Report was reviewed for errors due to changes for Independent Living enhancement.
Case Management - (Team 2) | 31532 |  |  | 269 | Ongoing Case Closure Checklist | IL Changes RPT269 CM16 Ongoing Case Closure Checklist (Form) | Report was reviewed for errors due to changes for Independent Living enhancement.
Case Management - (Team 2) | 31533 |  |  | 120 | Independent Living Plan Summary | IL Changes RPT120_CM44_Independent Living Summary | The Independent Living Report has been updated with new fields to match the new IL functionality
Case Management - (Team 2) | 30432 |  |  |  |  | CM53 - Add EY and FT Plans to items that prevent Case Merge | When a FT Plan or Emancipated Youth Plan exists on a case, case merge cannot be performed.
Case Management - (Team 2) | 30433 |  |  |  |  | PM04 - Person Merge | If the Removed Person has a EY, FT or IL Plan, the Person ID is switched to the Retained Person ID.
Case Management - (Team 2) | 30526 |  |  |  |  | CM44 - Add ref data values for the Assessment Tool Dropdown | Text box now displays if 'Other' is selected as the Assessment tool used.
Case Management - (Team 2) | 30590 |  |  |  |  | CM44 - IL Contacts List Page changes | New Functionality added to the contact directory. Contacts now display alphabetically by first name; and users are able to activate or deactivate.
Case Management - (Team 2) | 30027 |  |  |  |  | CM41 - Move Credit Report records from being recorded in Case Review | New Functionality - the Credit Reporting information are now stored within the IL record. The credit report pulls from the Independent Living Plan to the Case Review.
Case Management - (Team 2) | 29908 |  |  |  |  | CM41 - SAR is currently pulling IL Readiness Reviews that are outside the Review Period | Case Review/SAR now pulls IL Readiness Review records that are 90 days prior to the Approval Date of the Case Review/SAR.
Case Management - (Team 2) | 29966 |  |  |  |  | CM44 With the creation of the Final Transition Plan only Adoption Case Participants (Not AI members) populate dropdown | Adoption Members are now the only names in the drop list in the Final Transition Living Plan.
Case Management - (Team 2) | 30422 |  |  |  |  | CM44 - Create notification for Final Transition Plan | Notification is sent to the IL Worker and Primary worker for Final Transition Plan based on the IL Plan's Anticipated Emancipation Date entered.
Case Management - (Team 2) | 30425 |  |  |  |  | CM17 - Add Validation at Closure for FT and EY Plans | An Unresolved Topic Validation added if there is a non-end-dated Final Transition Plan for Active Case/Adoption Members or a non-end-dated Emancipated Youth Plan.
Case Management - (Team 2) | 30426 |  |  |  |  | CM17a - Add Validation at Closure for FT and EY Plans | User receives a validation error if there is an non-end dated FT plan or Emancipated Youth Plan.
Case Management - (Team 2) | 30427 |  |  |  |  | CM17b - Add validation in Adoption Case Closure for FT and EY Plans | A validation has been added prohibiting an adoption case closure when there is an active or pending IL plan, a non-end dated Final Transition plan, and/or non-end dated EY Plan.
Case Management - (Team 2) | 27865 |  |  |  |  | CM44 - Change fields on the Goal Details screen in the Independent Living Plan | New Functionality to the Goal Details page. This page lists Active goals with Case services linked and Completed Goals with date completed. Created in Error functionality has been added.
Case Management - (Team 2) | 27425 | 47992 | 48--Lucas |  |  | Enhancement Request-Activity Logs | New Functionality - Credit Report history is stored under the Credit report tab, not through an AL. Changes made to the new Credit Report tab captures this information.
Case Management - (Team 2) | 28225 |  |  |  |  | Create Tickler for Credit Reporting | Ticklers for Credit report are removed when 3 credit reports have been entered in the Credit Report record.
Case Management - (Team 2) | 27962 |  |  |  |  | CM44 - Changes to the IL filter screen | New Filter criteria added to the Independent Living Plan page.
Case Management - (Team 2) | 27969 |  |  |  |  | CM44 - Create Final Transition Plan in SACWIS | New Functionality- Final Transition Plan created to record youth who have emancipated from custody.
Case Management - (Team 2) | 27970 |  |  |  |  | CM44 - Changes to the Independent Living tab | ILP Youth Information and Assessment page have been either changed, updated or removed. The Assessment tool is now a dropdown what displays dynamically, 'Youth was informed that they may be a part of a cohort study' has been moved to NYTD Account Details screen and two grids have been developed for Assessment Information and Plan Information.
Case Management - (Team 2) | 26343 |  |  |  |  | Add Activity Log Validations for Conflicting Contact Types/SubCategories | Activity Logs now throws a validation when a user attempts to select contact Types that are non-congruent with the sub-categories. The Validation Message is "The [Contact Type] Contact Type is not applicable to the [Sub-Category] Sub-Category."
Case Management - (Team 2) | 26984 |  |  |  |  | CM44 - Remove NYTD tab from IL Plan and moving to NYTD hyperlink | NYTD Hyperlink is on the Independent Living Records screen.
Case Management - (Team 2) | 26985 |  |  |  |  | CM44 - 'Delete' hyperlink is not available if NYTD Account has been generated | The 'Delete' icon is not available once the NYTD Account has been generated.
Case Management - (Team 2) | 27344 |  |  |  |  | CM30 - Add Ability to Add Credit Check Documentation in Activity Log | New Functionality - Credit Report history is stored under the Credit report tab, not through an AL. User are now able to determine when the last CR was requested.
Case Management - (Team 2) | 27056 |  |  |  |  | CM44 - Add New Fields for Contact Details screen in the Independent Living Plan | New Functionality - Contact now displays in a list form and is ordered by modified date descending. Added fields- Relationship, Search Person, Address Search, Other Contact Information. New Requirements added to save a contact-Contact Name, relationship to Youth and one of the following: Contact Address, Contact Type and Contact or Other Contact Information.
Case Management - (Team 2) | 12958 | 49815 | 39--Huron |  |  | Master Defect for NYTD | The NYTD Tab on an Independent Living Plan now retains the date that the child was entered into the NYTD System.
Case Management - (Team 2) | 14533 | 56822 | 25--Franklin |  |  | CM44 - Credit Report Filter changes | New functionality to the Credit Report filter screen.
Case Management - (Team 2) | 15775 | 63819 | 57--Montgomery |  |  | CM44 - Create Emancipated Youth Plan in SACWIS | New Functionality: Emancipated Youth Plan created.
Case Management - (Team 2) | 21091 |  |  |  |  | CM44 - Credit Report information for youth needs to be updated | New Functionality - the Credit Reporting information is now stored within the IL record. Credit Report tab is on the filter list page.
Case Management - (Team 2) | 21153 |  | 04--Ashtabula |  |  | CM44 - Correct Independent Living Readiness Review Date | New Functionality - A future date can no longer be used in the Readiness Review. It must be <= to system date.
Case Management - (Team 2) | 20573 |  |  |  |  | CM44 - Change Independent Living Plan required fields | New Functionality- There are new required fields in the IL plan to make the plan active. Two major requirement changes- Only one goal and one contact is required in order to make the plan active.
Case Management - (Team 2) | 24137 |  |  |  |  | CM44 - Goal Topics – Independent Living | New Functionality - The Independent Living Goals Tab now displays 2 grids, the Current Plan grid and the Completed Goals grid.
Case Management - (Team 2) | 24563 |  |  |  |  | CM44 - Add NYTD Link | New Functionality - NYTD Hyperlink is now on the Independent Living Records screen.
Case Management/Adoption - (Team 2/3) | 30429 |  |  |  |  | CM20g - Add validation for Adoption Finalization for FT and EY Plans | A validation has been added prohibiting a child adoption finalization when there is an active or pending IL plan, a non-end dated Final Transition plan, and/or non-end dated EY Plan.
Case Management/Adoption - (Team 2/3) | 29967 |  |  |  |  | CM20a The new Final Transition Plan needs to move to the Adoption Case upon creation | If an Open Final Transition Plan exists within an Ongoing case, it now copy's into the Adoption case at time of adoption case creation/ association.
Case Management/Adoption - (Team 2/3) | 30431 |  |  |  |  | CM20b - Add validation message when user inactivates an Adoption Case Member | A validation has been added prohibiting an adoption case member from being inactivated when there is an active or pending IL plan, a non-end dated Final Transition plan, and/or non-end dated EY Plan.
Resource Management - (Team 3) | 22877 |  | 00--State |  |  | RM30-A new home study cannot be started until the home study for the same provider type is final approved or denied. | SACWIS now prevents user from beginning a new home study until the home study for the same provider type is final approved or denied. In addition, SACWIS system also prevents user from changing an existing home study disposition back to pending status when another home study of the same provider type is in pending status.
Resource Management - (Team 3) | 23433 |  |  |  |  | RM02 Validate against 'draft' activity log for logged in Agency. | Users now unable to add a status of 'close' to a provider record if draft activity log(s) exists on the provider record.
Resource Management - (Team 3) | 23558 |  |  |  |  | Provider Assignment change | In the Provider Assignment Information area on the Provider Overview screen, only one assignment displays now per worker with multiple roles displayed for that assignment. This change was made to correspond with the case assignment display in SACWIS.
Resource Management - (Team 3) | 23112 |  |  |  |  | RM02 Allow multiple Adoptive Care-International provider Types on a Provider. | Multiple Adoptive Care International provider types can now be linked through the inquiry process to a Provider record, if agency is different.
Resource Management - (Team 3) | 23063 |  |  |  |  | RM30 Ethnicity value cannot be 'Unable to Determine' for any applicants. | Users are now unable to validate a home study if applicant(s) have an ethnicity value of 'Unable to Determine'. User will need to update this value, as appropriate for each applicant.
Administration - (Team 4) | 30297 |  |  |  |  | CF10 - Create IL Worker Role | The existing Independent Living – Caseworker role has been changed to Independent Living – IL Worker role to allow users to be assigned to a case with the role of IL Worker.
Administration - (Team 4) | 2570 |  |  |  |  | Do not display mapping default and if a required field, do not display a blank in the dropdowns | ‘Mapping default’ removed as a drop down value for Provider Search and Provider Match screens.
Administration - (Team 4) | 11714 | 45115 | 48--Lucas |  |  | Login Screen Change Enhancement Request | ‘Reset My Password’ checkbox moved farther from login button. A confirmation message appears when ‘Reset My Password’ checkbox is selected and login button is clicked.
Administration - (Team 4) | 31065 |  |  |  |  | CM 44 Add security profile/user group of Closed Case IL Worker and Unassigned IL Worker | New user group of Closed Case IL Worker has been created to allow users to update NYTD and Credit Reports on closed cases. This security will be given to users that currently have the security of Closed/Sealed Adoption Case Viewer. New user group of Unassigned IL Worker has been created for workers that are not assigned to cases to have the ability to access IL Plan.
Reporting (Team 6) | 31837 |  |  | 358 | NYTD Statistical Report | RPT 358 - NYTD Statistical Report | A new column has been added to capture NYTD Survey exceptions recorded by users.
Defects Against Existing Functionality
Intake Management - Person (Team 1) | 14146 | 55156 | 57--Montgomery |  |  | IN12 - Add claim functionality to intake workload | Claim feature has been added to the intake workload. A worker must claim the intake in order to edit. If another user has already claimed the intake and another attempts to claim, a pop-up message appears to alert the worker. They can choose to open the record in view only or proceed to edit. This change prevents narratives and data from being lost when worker A is in the process of completing an intake and worker B opens the same intake.
Intake Management - Person (Team 1) | 18612 | 73136 | 55--Miami |  |  | IN03 - Intake Status is not Being Updated When Screening Decision is Made | Intake status now correctly updates when screening decision is saved. (Previously, intakes were sometimes stuck in 'pending' status after screening decision.)
Intake Management - Person (Team 1) | 22217 |  |  |  |  | IN01a - Do not allow sexual abuse to be added to a screened in AR intake | An Intake type of Sexual Abuse can no longer be added to an intake that has been Screened In AR.
Intake Management - Person (Team 1) | 24366 |  |  |  |  | IN01 - PARTICIPANT - Names not displaying on the add participant screen | When recording an intake participant, if user entered "Unknown" in both first name and last name fields, clicked OK, then clicked edit for that intake participant record, the first/last name fields would be empty. This issue has been resolved in the intake redesign.
Intake Management - Person (Team 1) | 24723 |  |  |  |  | IN01 - Intake validation issues | System now execute all intake validations upon marking the intake complete. Once the intake is complete, only the decision tab and comments are editable. In order to edit any of the intake content, the intake must be returned to pending status.
Intake Management - Person (Team 1) | 25953 |  |  |  |  | IN03 - Java error when screening in AR after deleting participants | Previously, when participants were deleted, then the intake was marked completed, and the screening decision Screened In AR was made without any save/apply in between, a java error resulted. This issue has been resolved.
Intake Management - Person (Team 1) | 26486 |  |  |  |  | IN01a - Unable to correct screening decision on FINS non-lead types | Screening decision can now be corrected on FINS/Non-lead Intake within 24 hours of Screening Decision.
Intake Management - Person (Team 1) | 26492 |  | 00--State |  |  | IN01 - Anonymous reporter phone number does not save | Reporter phone number was not saving when the reporter is Anonymous. This has been corrected so contact info will consistently save.
Intake Management - Person (Team 1) | 26732 |  |  |  |  | Java navigating from intake participant to other intake | When navigating via hyperlinks from an intake participant, to another intake from the person SACWIS history, a java error would result. This has been resolved so user can navigate without error.
Intake Management - Person (Team 1) | 26981 |  |  |  |  | Java error on screening decision edit | Java error no longer received when Screening Decision is changed from Screened In AR to Screened In TR.
Intake Management - Person (Team 1) | 27025 |  |  |  |  | IN01- Validation issues when changing intake category/type | When user accessed a completed intake on the workload and changed category/type, system displayed a warning message that non-applicable data would be removed. However, validations were still displayed pertaining to the removed allegations and original intake category/type. This has been resolved in the intake redesign.
Intake Management - Person (Team 1) | 27145 | 0046957 | 60--Muskingum |  |  | PM01 - Notification Sent in Error | The correct user who modified the information for AKA names and Marital Details of a provider now displays in the notification.
Intake Management - Person (Team 1) | 27267 |  |  |  |  | CM49- Ongoing AI safety plan discontinue date issue | For the Ongoing A/I, the Safety Response has been fixed to retain the discontinue selection and date.
Intake Management - Person (Team 1) | 27454 |  |  |  |  | IN01- Allegation validation fail | Validation upon marking intake complete should check that all ASRs and CSRs are accounted for in the Allegations. System was only checking that the participant was included in at least one allegation, but was not checking for the appropriate role. This has been resolved.
Intake Management - Person (Team 1) | 27463 |  | 25--Franklin |  |  | IN01a- Unknown Participant name updates issue | When the person record of the unknown participant is updated with the correct name, the name is supposed to display with a green carrot underneath 'Unknown' on the Intake Participants page. However, this is only displaying when the intake is linked to a case. If the Intake is viewed on the workload, the change does not display. This has been resolved.
Intake Management - Person (Team 1) | 27471 |  |  |  |  | IN03- ACV/AP Roles not updated to CSR/ASR when Intake Screened In AR | System corrected so that Screened in AR intakes always have CSR/ASR roles.
Intake Management - Person (Team 1) | 28580 |  |  |  |  | IN01 - Validation for Matching Intake Type and Allegations | System now validates at the time of intake completion to ensure that all Intake Types have a matching Allegation.
Intake Management - Person (Team 1) | 32907 |  | 00--State | 1 | JFS 01647 - Face Sheet | RPT001_ODJFS1647 | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32908 |  |  | 7 | JFS 01440 - PSA Alert | RPT 007 Court Complaint | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32909 |  |  | 118 | Activity Log Detail Report | RPT 118 CM30 Activity Log Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32910 |  |  | 119 | Activity Report | RPT 119 Activity Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32911 |  | 00--State | 2 | Safety Assessment Report | RPT002_Safety_Assessment | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32912 |  |  | 123A | Weekly Flash - Part A. Intake Statistics | RPT 123 Weekly Flash Part A Intake Statistics | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32913 |  |  | 128A | Program Area Monthly Statistical Report - Part A. Intake Statistics | RPT 128 Part A New Open Closed | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32914 |  | 00--State | 4 | JFS 01400 Family Assessment Report | RPT004_Family_Risk_Assessment | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32915 |  |  | 128B | Program Area Monthly Statistical Report - Part B. Ongoing/Adoption Case Statistics | RPT 128 Part B Case by Category Transferred | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32916 |  |  | 128C | Program Area Monthly Statistical Report - Part C. Custody Statistics | RPT 128 Part C Custody Stats | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32917 |  | 00--State | 5 | JFS 01403 Specialized Assessment | RPT005_Specialized_Assessment | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32918 |  |  | 154 | Rules Violation Summary Report | RPT 154 Rule Violation Summary | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32919 |  |  | 181 | JFS 01645 Part II VAC 1st & 2nd Extension Report | RPT 181 Agreement For Temporary Custody | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32920 |  | 00--State | 6 | JFS 01402 - Ongoing Case Assessment | RPT006_Ongoing_Case_Assessment | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32922 |  |  | 236 | Children Services Quarterly Statistical Report | RPT 236 Children Services Quarterly Statistical Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32924 |  |  | 253 | NCANDS Actual | RPT 253 NCANDS | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32925 |  |  | 275 | Notice of Perpetrator Match Found | RPT 275 Notice of Perpetrator | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32926 |  | 00--State | 23 | P-G-C Disposition Letter | RPT023_Parent_Guardian_Caretaker_Disposition_Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32927 |  |  | 299 | Intake Statistical Report by Geographical Designation Report | RPT 299 Intake Stats by Geo Location | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32928 |  |  | 325 | Intake Details & Statistics | RPT 325 Intake Details Statistics | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32929 |  | 00--State | 24 | ACV Disposition Letter Report | RPT024_ACV_DISPOSITION | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32930 |  |  | 328 | Alternative Response Mandated Reporter Letter | RPT 328 Alternative Response Mandated Reporter Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32931 |  |  | 330 | End Assessment Mandated Reporter Letter | RPT 330 End Assessment Mandated Reporter Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32932 |  | 00--State | 28 | Mandated Reporter letter - Initial | RPT028_R02_Mandated_Reporter_Letter_Initial | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32933 |  |  | 333 | AR Family Service Plan Report | RPT 333 AR Family Service Plan | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32934 |  |  | 370 | Provider Maltreatment Licensing Violation Report | RPT 370 Provider Maltreatment Licensing Violation Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32935 |  |  | 374A | Permanency Roundtable Skills Case Summary Form A | RPT 374A Permanency Roundtable Skills Case Summary Form | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32936 |  | 00--State | 30 | Mandated Report Letter - Disposition | RPT030_Mandated_Reporter_Letter_Disposition | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32937 |  |  | 382 | Safety Hazard Report | RPT 382 Safety Hazard Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32938 |  | 00--State | 31 | Cross Referral Notification Letter | RPT031_Cross_Referral_Notification_Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32939 |  |  | 389 | Family Assessment Risk Contributor Report | RPT 389 Family Assessment Risk Contributor Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32940 |  |  | 390 | Screening Decision Timeliness Report | RPT 390 Screening Decision Timeliness Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32941 |  | 00--State | 33 | Disposition Letter to Licensing/Supervising Authority | RPT033_Licensing_Supervising_Authority_Disposition_Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32942 |  |  | 405 | Intake Designated Drug Type Report | RPT 405 Intake Designated Drug Type Report | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32943 |  | 00--State | 34 | OHC Entity Administrator/Owner Disposition Letter | RPT034_OHC_Entity_Administrator_Owner_Disposition_Letter | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32945 |  | 00--State | 48 | AI Checklist | RPT048_INV_TRNSFR_CHKLST | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32946 |  | 00--State | 50 | Intake Log | RPT050_Intake_Log | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32947 |  | 00--State | 56 | Person Overview Report | RPT056_Person_Overview | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32948 |  | 00--State | 68 | JFS 01413 - Maintain Case Review Report | RPT068_JFS1413_Case Review form | Report was reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 32155 |  |  |  |  | IV18- Unknown participant names displaying incorrectly | If the Unknown participant names have been updated on the person records prior to linking the intake to a case, upon link, the corrected names were still showing as Unknown. The system now correctly displays the updated names. If one of these updated Unknown persons was selected as CRP, the case was created with the case name 'Unknown,' even though the CRP's correct name displays in the case members of the case. This has also been fixed so the correct name displays.
Intake Management - Person (Team 1) | 32402 |  |  |  |  | IV22- Selected harm description does not change | When changing an intake disposition, the harm description changes were not saving correctly. This has been fixed.
Intake Management - Person (Team 1) | 32539 |  |  |  |  | IN01 - Validations Missing Upon Completion | Validations to complete an intake were not working if the user marked the complete checkbox without applying or saving the intake first. This has been resolved with the intake redesign.
Intake Management - Person (Team 1) | 32761 |  | 00--State |  |  | PM02- Updates to county code | In build 3.04, county code 00 was changed from "State" to "Out of State," which had a negative impact on other areas which used 00 to delineate the state agency, ODJFS. Therefore, county code 00 is being changed back to "State" and code 99 is being added for "Out of State."
Intake Management - Person (Team 1) | 32974 |  |  |  |  | PM01b Medical Provider and Treatment Tab Incorrectly marked as Created in Error | Due to a defect, when a validation prevented a person medical provider from being marked created in error, the created in error checkbox would remain checked. Then if an associated treatment record was marked created in error, the system would automatically make the provider created in error as well. This has been corrected so the validations and the created in error validations work correctly.
Intake Management - Person (Team 1) | 33024 |  |  |  |  | IN02- Copy contact does not work for non-phone type | Copy contact now works correctly for non-phone contact types.
Intake Management - Person (Team 1) | 33042 |  |  |  |  | Pertinent Allegation validation missing for Stranger Danger intakes | System now validates for at least one allegation to be marked as "pertinent to the child fatality..." when the intake type is Stranger Danger and the fatality/near fatality question is answered Yes, as it does for CA/N reports.
Intake Management - Person (Team 1) | 33221 |  | 00--State |  |  | IV24- View link missing from Fatality-Near Fatality record | Child Fatality/Near Fatality records now have a view link. Previously, the link was not consistently present.
Intake Management - Person (Team 1) | 33038 |  |  |  |  | PM01c - Move Add Resources button | "Add Resource" button has been moved so it no longer overlaps the Type drop-down box.
Intake Management - Person (Team 1) | 32770 |  |  |  |  | PM02a- Create Address Broker message | Users encountered an error when Address Broker was down and they were unable to add addresses. System should instead display a message: "Address Broker is unavailable at this time. Please try again later."
Intake Management - Person (Team 1) | 32329 |  |  |  |  | IN01 - Drug Conversion for Existing Intakes | As a result of intake redesign, existing data conversion is needed. The Law Enforcement Involvement checkbox has been changed to a code in the database. For intakes with existing drug types selected, the following conversion rules are applied, depending on the status of the intake: For ‘Completed’ or decisioned Intakes with selected Drug Types, the radio button for "Is parental or caregiver substance abuse being reported by the referent?" will be set to ‘Yes’ and ‘Historical Drug Types Recorded’ will be populated for the "How did the reporter become aware of the substance abuse?" question. (this value is only available for legacy intakes) For Decisioned Intakes without any selected Drug Types, the default of ‘None Selected’ will remain in place for the question "Is parental or caregiver substance abuse being reported by the referent?" and the validation will be skipped. For Completed Intakes without selected Drug Types, user will get validation and have to put the intake back into pending to answer the question about parental/caregiver substance abuse.
Intake Management - Person (Team 1) | 32398 |  |  |  |  | PM02a - Navigating to Address Details on Address Search Causes Navigation Issue | The following navigation issues have been corrected: Domestic Address Search: When user searches for an address and then clicks on a returned address hyperlink to go to the Address Details page, they are given the option of hitting Save or Cancel to leave the details page. -if they hit Cancel, they are taken back out to a blank Address Search page. Hitting Cancel should return them to their previous address search results so they don't lose their address information. -if they hit Save, they are taken back out to the Person record Address tab with the address they had been looking at saved as an address record on the Person, even though they technically did not 'select' it. Save should save address details and return user to previous address search results. Foreign Address Search: When user searches for an address and then clicks on a returned address hyperlink to go to the Foreign Address Details page, they are given the option of hitting Close to leave the details page. -hitting Close takes the user back to a blank foreign address search page which should not happen. User should be taken back to the foreign address search results page they had navigated from without losing their search information.
Intake Management - Person (Team 1) | 32549 |  |  |  |  | PM04 - Person Merge Impacts on Global Navigation | When a person merge is completed, if the removed person is listed on any user's Recent list, the list will be updated to show the retain person.
Intake Management - Person (Team 1) | 32061 |  |  |  |  | IN02 - Copy Address and Contact Updates | Copy Address and Contact pages have been updated with Intake Redesign.
Intake Management - Person (Team 1) | 28690 |  |  |  |  | IN01 - Missing Allegation Causes White Screen on Save | If user removed allegations from a completed intake, then navigated to the OHC tab and saved, system would go to a blank white screen. This has been resolved with intake redesign.
Intake Management - Person (Team 1) | 28507 |  | 00--State |  |  | IN01a - Adding AP/ACV Participants to Screened Out Intake | Screened Out intakes are frozen at Screening Decision and no additional edits can be made other than changing the Screening Decision within 24 hours.
Intake Management - Person (Team 1) | 28294 |  |  |  |  | IN01 - PARTICIPANT - Need Race Validation on Add Participant | The intake participant details page now includes all race values and applicable validations to align with the person record.
Intake Management - Person (Team 1) | 29178 |  |  |  |  | IN01 - Research Checkbox Enabled after Intake is Completed | With Intake Redesign, the intake status is being moved to a dropdown, vs. checkboxes. If intake is in Completed Status and user changes dropdown selection to Research or Pending, then the intake status will be updated accordingly and the Decision tab will not be accessible.
Intake Management - Person (Team 1) | 28921 |  |  |  |  | IN01 - Navigation Issues involving Specialized (formerly OHC) Tab | Navigation issues involving the Specialized (formerly OHC) tab of the intake have been resolved in the intake redesign. Original Steps to recreate in old Intake format: 1) Have two completed intakes on the workload 2) Access Intake #1 by hitting Decision link 3) Navigate to the OHC Tab and check the 3rd party box and select something from the 3rd party drop down (**In redesign, 3rd party info will be on Basic tab) 4) Hit 'Add Provider' at the bottom of the OHC tab (being renamed Specialized tab) and then hit Return to go back to the intake 5) Hit Save 6) Access Intake #2 in view mode by clicking on the Intake ID hyperlink 7) Navigate to the Participants Tab and hit 'Close' 8) The OHC Tab then appears on the Participants Tab with the 3rd party box checked
Intake Management - Person (Team 1) | 29474 |  |  |  |  | IN01 - Validation Message Needed for Dependency Participants | When a user enters a Dependency intake, a Child Subject of Report is required to complete but not an Adult Subject of Report. If the user completes the intake with only a CSR listed and the intake is screened, the intake cannot be linked to a new case because there is no adult available to be linked as a CRP. A validation has been added to require at least one participant in addition to the Child Subject of Report to complete a Dependency intake.
Intake Management - Person (Team 1) | 27348 |  |  |  |  | IN01b- ICPC IVE Medicaid History Grid display issue | The Medicaid Info tab of the ICPC record has been fixed so that the effective and termination dates for the child's IVE Medicaid history display.
Intake Management - Person (Team 1) | 28175 |  |  |  |  | IN01 - PARTICIPANT- Unknown Participant Information Not Updating | When adding an intake participant, if the user filled in the first and last name of the participant and hits OK, they were unable to then go back into the participant and edit to remove the name and mark the 'Unknown' check box. This has been resolved in the intake redesign.
Intake Management - Person (Team 1) | 26933 |  |  |  |  | IN01- REPORTER - Person ID clears when type is changed | If the user attempts to change the radio button from Non-Mandated or Mandated Reporter to Anonymous, and the person information was entered via person search or text entry, a warning message pop up will display, "The reporter name and contact information will not be retained if you change the type to Anonymous. Do you wish to continue?" OK/Cancel
Intake Management - Person (Team 1) | 25223 | 0043597 |  |  |  | IN01b - Discontinue ICPC Missing Information Notification | The notifications for missing ICPC information have been discontinued as they are no longer valid with ICPC being decentralized and managed at a county level.
Intake Management - Person (Team 1) | 25678 |  |  |  |  | IN01 - Intake Screens Stuck With Error Message | When other FINS intake types were selected with AR required non-lead contacts, system would sometimes get stuck on the Basic tab. This has been resolved with intake redesign.
Intake Management - Person (Team 1) | 22079 |  |  |  |  | IN01b - Send an email notification to the State ICAMA Administrator for each child receiving ICAMA on the first of the month the child will turn eighteen | An email notification is now sent to the State ICAMA Administrator on the first day of the month when a child turns 18 and is receiving ICAMA Medicaid.
Intake Management - Person (Team 1) | 22080 |  |  |  |  | IN01b - Send an email notification to the State ICAMA Administrator for each child receiving ICAMA on the first of the month the child will turn twenty-one | An email notification is now sent to the State ICAMA Administrator on the first day of the month when a child turns 21and is receiving ICAMA Medicaid.
Intake Management - Person (Team 1) | 23431 |  |  |  |  | PM03 - Search criteria clears when there is an SSN | Other search criteria is no longer being cleared when an SSN is entered on the Person Search screen.
Intake Management - Person (Team 1) | 27874 |  |  |  |  | IN01- Search Provider enabled in view mode on Completed Intake | Previously, fields on the Additional tab were enabled in view mode for intakes that were in completed status, even though no changes to the information would be saved. These fields have been relocated in the intake redesign and this issue has been resolved.
Intake Management - Person (Team 1) | 29431 |  |  |  |  | IN01 - Intake Type Validation Creates Navigation Issue | When AR required non lead contacts type was selected with any other type, users would at times get stuck on the Basic tab when validation messages were present. This has been resolved with intake redesign.
Intake Management - Person (Team 1) | 28544 |  |  |  |  | IN12 - Disable Add Intake Button | The 'Add Intake' button is now disabled unless the user has 'Screener' security. Screenshots attached.
Intake Management - Person (Team 1) | 31189 |  |  | 56 | Person Overview Report | RPT 056 - Parameters Page Select All Checkbox doesn't unselect all | On the Parameters page for Person Overview report, the 'Select All' checkbox now correctly clears all selections if the user unchecks it.
Intake Management - Person (Team 1) | 33050 |  |  |  |  | PM01- Correct person characteristic validation message | Person Characteristic's Diagnosed By validation message has been corrected.
Case Management - (Team 2) | 18333 | 72437 | 76--Stark |  |  | CM44 - Independent Living Record Readiness Review Change Enhancement | Readiness Review narrative textbox has been increased to 10,000 characters.
Case Management - (Team 2) | 27531 |  | 00--State |  |  | CM51 - Add Case Load Count Number Next to Worker(s) Name | The number of case assignments for each worker is now displayed on the Assignments screen
Case Management - (Team 2) | 29692 |  |  |  |  | CM05 - When Amending a Finalized Recommended Case Plan user receives a Java | User no longer receives a Java error when amending a finalized recommended case plan. The system will display the correct Case Plan Topics based on the child’s current Agency Legal Status or Placement Type.
Case Management - (Team 2) | 30697 |  |  |  |  | CM41 - Java Error when Approving a Case Review/SAR | Java error has been resolved on the CR/SAR
Case Management - (Team 2) | 30807 |  |  |  |  | CM05 - No edit link on a Case Plan Amendment when In Progress | The edit hyperlink was missing when there was a Case Plan Amendment in a Status of In Progress of an Initial Recommended Case Plan. The edit link is restored on the in progress case plan record.
Case Management - (Team 2) | 32715 |  |  |  |  | CM17 - System closing case upon routing for approval | Routed task history functionality fixed to prevent system from closing case upon routing for approval.
Case Management - (Team 2) | 33043 | 0056223 | 47--Lorain |  |  | Unable to enter AL on cell phone | Phone issues fixed; users are now able to enter an Activity log on a cell phone
Case Management - (Team 2) | 32905 |  |  |  |  | CM09 - Placement Information issues for Recommended Case Plans | The system now displays the correct Case Plan Topics based on the child’s current Agency Legal Status or Placement Type.
Case Management - (Team 2) | 33386 |  | 00--State |  |  | CM04 - Java displaying on Living Arrangement when displayed on provider record | JAVA error has been fixed and no longer displays on the Living Arrangement link on the provider record.
Case Management - (Team 2) | 32816 |  |  |  |  | CM44 - IL Plan validation issues on Closed records | Navigation issues fixed on closed converted case with an IL plan.
Case Management - (Team 2) | 32550 |  |  |  |  | CM53 - Case Merge Impact on Global Navigation | Case Merge Business Rules added to the Intake Functionality
Case Management - (Team 2) | 32462 |  |  |  |  | Change Case Plan type 'Amended Recommended' | Case Plan Type of 'Amended Recommended' was missing the space between the words and has been corrected.
Case Management - (Team 2) | 31201 |  |  |  |  | CM01h Complaint and Motions Court Name is a Required field | The Court Name is a required field when entering a Create Complaint Record, a Record Complaint Record, a Create Motion Record and a Record Motion record.
Case Management - (Team 2) | 29613 |  |  |  |  | CM05 - Case Plan Validation Error not checking if Case Plan has Recommended Flag | The user no longer receives a Validation error for Placement Information when attempting to finalize their Recommended Case Plan with no placement/initial removal recorded or recommended on the Identifying Information screen.
Case Management - (Team 2) | 32850 |  |  | 392 | Identified Fathers Report | RPT 392 - System selecting all child records on Parameter screen: On the Identified Father's Parameter screen, when a user unchecks one or more of the child records and then selects a value in the Father Identified dropdown, the system checks the child record boxes again. | System now only checks the children that the user selects.
Case Management/Adoption - (Team 2/3) | 28425 |  |  |  |  | CM20g New Validation at time of Adoption Seal for any child in NYTD | A new validation message has been added when a child finalizes from within an Adoption Case, the Finalization checklist will ensure the youth does not have an Active or Pending IL Plan or an non-end-dated Final Transition Plan.
Case Management/Adoption - (Team 2/3) | 28429 |  |  |  |  | CM20a Copy the NYTD information at time of adoption case creation | The NYTD information (that goes along with the IL Plan) now copy's to the adoption case at the time of adoption case creation (if one already exists).
Case Management/Adoption - (Team 2/3) | 32799 |  |  |  |  | CM20f Prefinalization Adoption Assessment Record - Additional Family Information tab spell check does not work on expand full screen | The spell check features now works on the Pre finalization Adoption Assessment Record - Additional Family Information tab.
Resource Management - (Team 3) | 33089 |  |  | 350 | MEPA Provider Report | RPT 350 MEPA Provider Report | MEPA Provider Report now only generates in an Excel format; not PDF
Resource Management - (Team 3) | 33234 |  | 00--State |  |  | RM03 - Code changes and ref data changes needed for training competencies | In the provider training link, competencies were updated and were sorted based on Pre-Service trainings and Ongoing/Continuing trainings to make it easier for users to select the appropriate training competencies.
Resource Management - (Team 3) | 33260 |  | 00--State |  |  | RM02c - Provider cannot be closed when in progress or pending home study exist | In provider record, if in progress or pending approval home study(s) exist, user will be unable to close the provider record.
Resource Management - (Team 3) | 32551 |  |  |  |  | RM35 - Merge Provider Impact on Global Navigation | Online Provider merge will display as follows on the Recently Accessed List; If only Retain Provider is on the Recently Accessed list, then on merge there is no update. If only Remove Provider is on the Recently Accessed List then it will be updated with the Retain Provider ID. If both Retain and Remove Provider item(s) accessed by logged user are on the list then – If Retain Provider is the most recently accessed then keep the retain and delete the remove Provider. If Remove Provider is the most recently accessed, then update the remove to retain and delete the retain.
Resource Management - (Team 3) | 32552 |  |  |  |  | RM38 - Non-ODJFS Merge Impact on Global Navigation | Non-ODJFS Provider merge will display as follows on the Recently Accessed List; If only Retain Provider is on the Recently Accessed list, then on merge there is no update. If only Remove Provider is on the Recently Accessed List then it will be updated with the Retain Provider ID. If both Retain and Remove Provider item(s) accessed by logged user are on the list then – If Retain Provider is the most recently accessed then keep the retain and delete the remove Provider. If Remove Provider is the most recently accessed, then update the remove to retain and delete the retain.
Resource Management - (Team 3) | 32622 | 56183 | 25--Franklin |  |  | Provider AKA Does Not Display in View Mode | When a user views a NON-ODJFS Provider record, the "Provider AKA Name Information section" now displays from the Provider Search result area.
Resource Management - (Team 3) | 32843 |  |  |  |  | Basic information is no longer being displayed when there has been a provider merge. | From the Home Study Link, "Provider Basic information" now displays when there has been a provider merge.
Resource Management - (Team 3) | 22172 |  |  |  |  | RM09: FC Exit Interview Hyperlink should not display on current (non end-dated) placement records | Exit Interview Hyperlink no longer displays on current (non end-dated) placement records.
Resource Management - (Team 3) | 23377 |  |  |  |  | PM01 Validation message on inquiry is incorrect. | Validation message has been corrected to read: "Validation message(s) We found a few areas that need your attention: This inquiry cannot be linked to the selected provider record, there is already an open provider type for this agency on this provider record."
Resource Management - (Team 3) | 22220 |  |  |  |  | RM30-Home Study disposition and disposition date change needed | When Home study is 'recalled' or 'declined for rework', the home study recommendation now reverts back to a 'pending' status and the recommendation date is made null.
Administration - (Team 4) | 26840 |  |  |  |  | PM04- Person Merge did not retain deceased date unknown checkbox | The deceased date unknown flag is retained from the remove person when selected by the users.
Administration - (Team 4) | 31420 |  |  |  |  | CF24 – RWD Issue – Maintain Agency | The Name search field size has been adjusted on the Agency Search screen to fit inside container size when using mobile devices.
Administration - (Team 4) | 31444 |  |  |  |  | Case Review Approval Routing Returns to Case Workload | When user selects a routed case review they are taken directly to the case review for approval.
Administration - (Team 4) | 25153 | 0043305 | 25--Franklin |  |  | PM04 - Person merge issue with Unknown DOB | The removed person’s DOB is retained when user selects to have the removed person DOB retained during person merge, where the retained person DOB has the Unknown DOB box checked.
Administration - (Team 4) | 31418 |  |  |  |  | RWD - CF10 Create Initial Case Assignment date field missing calendar | The date calendar has been added back to Create Initial Assignment screen next to the Start Date field.
Administration - (Team 4) | 30852 |  | 76--Stark |  |  | CF36a - Move "Reset my password" check box | The ‘Reset my password’ checkbox has been moved farther from the login button to avoid accidental resetting of password.
Financial Management (Team 5) | 32542 |  |  |  |  | FM13 Transaction Date error in client benefits | This defect was created to prevent a validation message from occurring in the Client Benefits area of Financial when the Transaction Date falls outside of the Benefit Payment Begin Date and Benefit Payment End Date. The defect also now prevents a validation message from occurring when the Pay Date falls outside of the Benefit Payment Begin Date and Benefit Payment End Date.
Financial Management (Team 5) | 16159 |  |  | 416 | Eligibility Determination Report | New Report - FM20 - Eligibility Determination Report - Front End Work: A new report needs created to allow users to print eligibility and Reimburseability records. | The front end parameters are being added to allow the user to select a report option and generate. The user can select to print only the eligibility record, print the eligibility record and all corresponding Reimburseability records, print the eligibility record, all corresponding Reimburseability records, and the associated payment history, print just a payment history, or print a specific Reimburseability record.
Financial Management (Team 5) | 24694 |  |  |  |  | FM-S20 Perform Eligibility Determination: A new report needs created to allow users to print eligibility and Reimburseability records. | This defect creates the online printable reports. The user can select to print only the eligibility record, print the eligibility record and all corresponding Reimburseability records, print the eligibility record, all corresponding Reimburseability records, and the associated payment history, print just a payment history, or print a specific Reimburseability record.
Financial Management (Team 5) | 27919 |  |  |  |  | FM21 Annual Reasonable efforts to finalize permanency plan not being calculated correctly: 1. The system is inaccurately considering all reasonable efforts ruling values when determining the "reasonable efforts to finalize a permanency plan" requirement for Reimburseability redetermination purposes. 2. When updating the Reimburseability Record for a new value of Placement, counties are receiving a "NO" for 'Reasonable efforts to finalize the Permanency Plan were obtained in the appropriate time frame or are not due' when it should be "YES". | 1. When updating the Reimburseability Record for a new value of Placement, 'Reasonable efforts to finalize the Permanency Plan were obtained in the appropriate time frame or are not due' is displaying correctly as "Yes" if RE to Finalize is not yet required. 2. SACWIS is now accurately considering and displaying the correct "reasonable efforts to finalize a permanency plan" requirement for Reimburseability redetermination purposes.
Financial Management (Team 5) | 29903 | 0052583 | 55--Miami |  |  | FM20 - Error trying to complete Income/Resource worksheet: It appears that if an SFU member has more than one unearned income record you are getting an error when you try to search for the person on the Income/Resource worksheet section. | Users can complete the Income/Resource worksheet for SFU members that have more than 1 unearned income record.
Financial Management (Team 5) | 30984 | 53861 | 25--Franklin |  |  | RPT 239A - IV-E Disbursement Journal: When a disbursement month is entered on the parameters page the Disbursement Names do not populate on the Parameters for the report | Disbursement names now populate on the parameters section.
Financial Management (Team 5) | 31208 |  |  | 416 | Eligibility Determination Report | New Report - FM20- Eligibility Determination Report - Online | The new online Eligibility Determination Report generates successfully from the eligibility tab and the Financial Workload.
Financial Management (Team 5) | 26143 |  |  |  |  | FM20 Annual reasonable efforts notification | This defect was created to prevent the annual reasonable efforts due notification from being sent to state workers with eligibility specialist security when the county agency has legal custody of a child. The notification must only be sent to eligibility specialists of that specific county agency.
Financial Management (Team 5) | 31756 | 0054918 | 75--Shelby | 391 | IV-E Schedule A Cost Information Report | RM-S13 Maintain Provider Service Contracts / RPT 391 Amendment Report Increased Amount Display Issue: Changes are needed to the Add Amendment screen for the new Master Contract report. | Users can enter Amendments for Amount, Date, Amount and Date, Article, and Other.
Financial Management (Team 5) | 33367 | 0057308 | 51--Marion | 313 | Reimbursement Reconciliation Report | RPT 313 Not Displaying Correct Non-Recurring Adoption Subsidy Reimbursement: Non-recurring adoption subsidy reimbursement amount was not correct in Reconciliation Report (313). | The Reconciliation Report (313) now displays correct reimbursement amount for Non-recurring adoption subsidies.
Financial Management (Team 5) | 32955 |  |  | 313 | Reimbursement Reconciliation Report | RPT 313 Display type of payment in voucher dropdown: On the reconciliation report parameters page, there isn't a descriptor next to the pmt period in the voucher dropdown. | On the reconciliation report parameters page, a payment descriptor has been added next to the Pmt period in the voucher id dropdown.
Reporting (Team 6) | 33055 |  |  |  |  | Explore Impacts of Table changes with Reporting Team | No negative impacts were found. Note: This is a Quality Assurance Action that happens behind the scenes
Reporting (Team 6) | 22902 |  | 00--State | 401 | ICPC Statistical Report | NEW Rpt 401 ICPC Stat Rpt | RPT 401 has been created to help OFC Managers & Staff and County Staff manage the number and status of ICPC/ICAMA cases Open or Active during an identified timeframe.
Other Notes
Intake Management - Person (Team 1) | 32923 |  | 00--State |  |  | RPT022_Alleged_Perpetrator_Disposition | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Report reviewed for errors from table changes due to Intake enhancements.
Intake Management - Person (Team 1) | 33236 |  |  |  |  | IN01a- Error on Copy Address/Contact in Post-Decision Intake | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The copy contact/address was not working on a post-decision intake. This has been corrected.
Intake Management - Person (Team 1) | 33243 |  |  |  |  | Intake Typos in UAT | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - A few typographical errors found in initial UAT testing have been corrected.
Intake Management - Person (Team 1) | 33296 |  |  |  |  | Tab function between fields | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - On the ACV/AP details, Allegations, and Reporter pages in UAT, the Tab function from the keyboard was not moving the cursor from field to field. This has been corrected.
Intake Management - Person (Team 1) | 33404 |  | 00--State |  |  | IN01a- UAT issues on post decision intake | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The following issues were discovered in initial testing in UAT 3.06 and have been fixed: 1. If I add a post-decision narrative, then go to add another, the text from the first one is pre-filled. The text field should be blank on create. 2. On intakes created prior to 3.06, if I try to add any information to the intake, validations display for the newly added fields. System needs to skip these validations, as user cannot edit the fields and should not. 3. On Participant Roles page, options display which should not, based on business rules. ACV and AP can only be added to the intake within specified timeframe/prior to safety assessment. System is letting me select these roles, then will not allow me to delete them. On the Participant Details page, the roles appeared to be correct. 4. When I selected one role from Participant Details page, then added roles from the Participant Roles page, the roles did not display in hierarchical order according to business rules. System kept the first role selected from participant details as the primary role.
Intake Management - Person (Team 1) | 33413 |  | 00--State |  |  | IN03- Intake Decision tab issues in UAT | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - During initial testing of build 3.06, the intake decision tab was found to have pathway assignment fields for intakes other than CA/N, and the emergency field was enabled when it should not be. These issues have been corrected for the final build.
Intake Management - Person (Team 1) | 33423 |  | 00--State |  |  | IN01- Manually entered address does not save on Intake Participant | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - An address entered manually (rather than selected from the Google list) on the intake participant detail page was not saving. This has been resolved.
Intake Management - Person (Team 1) | 33425 |  |  |  |  | PM02- Address creation navigation issue | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - In initial testing for build 3.06 in UAT, upon save of a newly created address, the user was returned to the search page instead of the address being pulled back to the person. This has been corrected.
Intake Management - Person (Team 1) | 33436 |  |  |  |  | PM01- Intake Participant info needs to populate on Create New Person | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When a new person is created from intake participants, all the data that has been entered for the participant should pull forward into the new person except address and contact (since person must be saved before these fields can be saved). Address and contact can be populated to the new person via the Reconcile button on the participant detail page.
Intake Management - Person (Team 1) | 33491 |  | 00--State |  |  | IN01- Unknown intake participant data is not copied to the Person | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Information from the intake participant details page of an unknown participant was not being copied forward to the newly created person record. This has been fixed.
Intake Management - Person (Team 1) | 33501 |  | 00--State |  |  | IN01- ACV/AP detail validation where legacy page is complete | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The following validations will not apply to intakes once the screening decision is made: All Required ACV/CSR Information must exist to mark the Intake as complete (ACV/AP Detail). All Required AP/ASR Information must exist to mark the Intake as complete (ACV/AP Detail). **For intakes that remain in Complete status at the time the new functionality is deployed, users will receive the above validations even if ACV and AP information was entered on the old detail pages. Users will change the status back to pending to complete the ACV/AP detail tab, then put it back in Complete to enter the screening decision.
Intake Management - Person (Team 1) | 33502 |  | 00--State |  |  | IN12- Release link should only display for Complete intakes | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - On the intake workload, the release link was displaying for pending intakes claimed by a user with SDM security. The release link will only display for intakes that are Complete, and only for users with Screening Decision Maker security
Intake Management - Person (Team 1) | 33510 |  |  |  |  | IN01- Java error from Participants Tab | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - A java error resulted when I clicked Cancel from the Participants tab. Prior to clicking cancel, I had clicked the search links for one participant at a time, then canceled before or after conducting the search, without creating or selecting any person. I then navigated to Reporter and/or Basic tab, then back to Participants and hit Cancel. This has been resolved in final build.
Intake Management - Person (Team 1) | 33511 |  | 00--State |  |  | IN01- Intake participant search criteria not selecting | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The search criteria selection checkboxes on the intake participant page were not automatically selected for the available fields. This has been corrected such that on entering the search page, each field that has data will default to checked in the "Search Using" box.
Intake Management - Person (Team 1) | 33512 |  |  |  |  | IN01a- Navigation issue from intake linked to case | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When exiting an intake linked to a case, system navigated back to the intake workload instead of the intake list within the case. This has been resolved.
Intake Management - Person (Team 1) | 33517 |  |  |  |  | IN01a- Decision Correction Navigation Issue- UAT | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When state admin user corrects the intake received and/or decision date/time, system was navigating directly to the intake workload instead of back to the intake decision tab. This has been resolved.
Intake Management - Person (Team 1) | 33522 |  |  |  |  | IN01a- Inconsistent validation for post-decision narrative | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Post-decision narrative validation was not displaying consistently from all tabs. This has been corrected.
Intake Management - Person (Team 1) | 33552 |  |  |  |  | IN03 - Supervisor Name and Decision Date Not Displaying | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Screening Decision Maker name and date/time decision was recorded displays on the Decision tab after the decision has been saved.
Intake Management - Person (Team 1) | 33583 |  |  |  |  | IN03- UAT- Decision correction page has wrong font | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The Decision Correction comments section displayed the wring font. This has been corrected.
Intake Management - Person (Team 1) | 33584 |  |  |  |  | IN01- UAT- Third party type field displays in error upon complete | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - If third party and type were entered, if the question was then changed from Yes to No, the type of Third Party field would reappear upon completion of the intake. This has been corrected.
Intake Management - Person (Team 1) | 33585 |  |  |  |  | IN01- UAT- Intake header still shows claimed by worker after screening decision | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The intake header was showing the intake was claimed post-decision if the decision had been corrected to screened out. This has been resolved.
Intake Management - Person (Team 1) | 33332 |  |  |  |  | IN01- View access to intake decision tab is incorrectly restricted to SDM | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment -In UAT interim build, decision tab could only be seen by users with SDM security. Decision tab now displays without SDM security when intake has status of Linked or Removed. While on workload, only SDM has access to Decision tab.
Intake Management - Person (Team 1) | 33576 |  |  |  |  | IN03- Decision comments time stamp issue | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Upon save of the decision details, a tme stamp with the user's name is applied to the decision comments field, matching the date/time of the screening decision. If a decision correction is made, the correction comment also has a time stamp including the name of the user entering the correction.
Intake Management - Person (Team 1) | 33578 |  |  |  |  | IN01- Incorrect text displayed in UAT on ACV/AP Detail page | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - On ACV / AP DETAIL tab, under AP / ASR Details, there was an incorrect line of text displaying under the question, "What is the current access of the AP(s)/ASR(s) to each Alleged Child Victim/Child Subject of Report." This has been corrected prior to final build.
Intake Management - Person (Team 1) | 33621 |  | 00--State |  |  | IN03- Add SDM name to header post decision | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - At time of screening decision, the "Claimed" label in the intake header is replaced with "SDM: <Last Name, First Name>."
Intake Management - Person (Team 1) | 33622 |  | 00--State |  |  | IN01a- State Admin functionality in UAT | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The State System Administrator access to intakes post-screening decision has been restored.
Intake Management - Person (Team 1) | 33623 |  | 00--State |  |  | IN01a- UAT- ACV/AP tab checkboxes enabled in error | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Checkboxes on the ACV/AP detail page were enabled post-screening decision. This has been corrected.
Intake Management - Person (Team 1) | 33624 |  | 00--State |  |  | IN01- UAT- End screener claim upon complete status | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The screener's claim was not ending upon completion of the intake. This has been resolved.
Intake Management - Person (Team 1) | 33635 |  |  |  |  | IN01- UAT- Specialized badge, warning message, and data update | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Issues found in UAT related to the Specialized tab have been resolved. A warning message displays to alert user that any data entered on the specialized tab will be cleared upon completion of the intake if the category has been changed to something that is not compatible with Specialized, or if the Specialized A/I question on the Basic tab has been changed from Yes to No. The system no longer saves a blank record in the OHC table. "Number of children alleged perpetrator has access to must be a number" validation message was displaying on the wrong page, but has been corrected.
Intake Management - Person (Team 1) | 33637 |  | 00--State |  |  | IN01- UAT- Intake category change issue | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Changing the intake category from CA/N to FINS was no longer automatically defaulting the intake type to Stranger Danger (as it currently does in production). If user changes CA/N to FINS: 1. System should give warning message that allegations will be removed 2. On continue, system should automatically select Stranger Danger for the Type and remove allegations.
Intake Management - Person (Team 1) | 33638 |  | 00--State |  |  | IN01a- UAT- Prevent removal of intake types post-decision | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When Intake Category is FINS and one of the intake types selected is Required Non-Lead PCSA Interviews, system was allowing user to remove other selected intake types on edit from the workload. When other intake types have been selected along with Required Non-Lead PCSA Interviews, user cannot remove anyof the intake types from the intake, including the Required Non-Lead PCSA Interviews. When Required Non-Lead PCSA Interviews is the only intake type, it can be removed and replaced with Alternative response required non-lead PCSA contacts.
Intake Management - Person (Team 1) | 33646 |  |  |  |  | IN12- Claim warning displays in error in UAT | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - If user clicked edit/decision on an intake claimed by another user, then closed the claim warning message box, the claim warning message would subsequently display whenever user exited a subsequnt intake. This has been resolved.
Intake Management - Person (Team 1) | 33667 |  |  |  |  | IN01- UAT-Participant address cleared on save and add | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - On the intake participant details page, if there were validations when user clicked the save and add another button, the address field was getting cleared out. This has been resolved.
Intake Management - Person (Team 1) | 33668 |  |  |  |  | IN12- UAT- Claim should happen on decision tab for SDM | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When a completed intake is not claimed and the user clicks the decision tab, the claim should be applied.
Intake Management - Person (Team 1) | 33669 |  |  |  |  | IN12- UAT- Intake claim upon status change from complete to pending/research | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - When the SDM user changes the intake from completed to pending/research, the claim will remain with the SDM.
Case Management - (Team 2) | 33639 |  |  |  |  | CM44 Readiness Review delete Icon | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format changes - Removed trash can from a Readiness Review that is linked to an approved CR
Case Management - (Team 2) | 33631 |  |  |  |  | CM44 IL Plan- Goal Topics | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format Changes - List Current and Completed goals in Descending order.
Case Management - (Team 2) | 33579 |  |  |  |  | CM44 - NYTD Account screen should pull from IL Youth Account not Person ID | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The system now displays the youth's information as of the time that the account was created
Case Management - (Team 2) | 33339 |  |  |  |  | CM44 EY Plan Support Topics | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - (Support Topic Requested) in parenthesis next to the support topic when comments are entered or case services are linked.
Case Management - (Team 2) | 33588 |  |  |  |  | CM44 - Final Transition Plan Youth Information issues | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Updates made to the FT plan that include formatting Medication, Health Care Providers and Font adjustments.
Case Management - (Team 2) | 33589 |  |  |  |  | CM44 - Issues on Final Transition Plan Resources Tab | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format changes made to the FT Plan-Resource Tab
Case Management - (Team 2) | 33590 |  |  |  |  | CM44 - Final Transition Plan Necessary Documents Issues | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Date Health Care Power of Attorney reviewed is now showing as required (Necessary Documents).
Case Management - (Team 2) | 33597 |  |  |  |  | CM44 - Signature pages on IL, FT, and EY Plans | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The Add Outcome Response button now displays on the 17th birthdate until the last NYTD send date that occurs after the 17th birthday and more than 45 days have passed.
Case Management - (Team 2) | 33559 |  |  |  |  | CM44a NYTD Outcome Response button display issue | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Outcome Response button no longer displays if outcome is completed on time.
Case Management - (Team 2) | 33562 |  |  |  |  | CM44a NYTD Add Outcome Response | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format Changes - Add Outcome Response button now displays at the beginning of the FFY Period in which the youth’s 19th or 21st birthday occurs
Case Management - (Team 2) | 33570 |  |  |  |  | CM44 - NYTD Outcome Response button display issues | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The Add Outcome Response button now displays on the 17th birthdate until the last NYTD send date that occurs after the 17th birthday and more than 45 days have passed.
Case Management - (Team 2) | 33447 |  |  |  |  | CM44 Ipad issues | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format issues resolved. Button on page was not displaying correctly
Case Management - (Team 2) | 33463 |  |  |  |  | CM44 - Validation when adding a Contact when a Case Relationship doesn't exist | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Validation message added when a relationship is not recorded.
Case Management - (Team 2) | 33416 |  |  |  |  | CM44 - Allow State System Admin to edit all IL plans | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The State System Administrator can correct the Plan Developed Date, Plan Closed Date, and Status for the Independent Living Plan.
Case Management - (Team 2) | 33304 |  |  |  |  | CM44 - Validating for Existing Goal Details records | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Existing goals without linked Case Services now require a Goal Effective Date and Comments. The system displays a validation message if this occurs.
Case Management - (Team 2) | 33319 |  |  |  |  | CM44 - Edit rules for Contacts | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - The Permanent Adult Connection checkbox is always enabled unless contact is inactive.
Case Management - (Team 2) | 33159 |  |  |  |  | CM44 - Add tab to IL Plan Validations | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Corresponding tabs added to validation messages on the IL Plan.
Case Management - (Team 2) | 32784 |  |  |  |  | RPT 407 FT Plan- Generate Document Page | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Generate document (FT Plan) page added.
Case Management - (Team 2) | 32785 |  |  |  |  | RPT 409 Emancipated Youth- Generate Document Page | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Emancipated Youth Plan-Generate Document page added
Administration - (Team 4) | 33370 |  | 00--State |  |  | Updates to SACWIS footer | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Changes to the universal footer as follows: - Remove the Home hyperlink, since there is are two access points at top of page. - Remove environment name from the right side of the footer in the test environments, as it is displayed in the header. (Not applicable in production environment.)
Financial Management - (Team 5) | 33619 |  |  |  |  | RPT 409 Emancipated Youth Plan-updates/additions/corrections | Note: This issue was recorded while Release 3.06 was being tested in the SACWIS UAT Environment - Format Updates to RPT 409- EY plan